## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
sprint 1( 10/2/26) | sprint 1 (10/2/26) | girees_K_233 | I want to collect Aadhaar, PAN, Passport images so that models can be trained accurately. | MUST HAVE | Roboflow website | A Gireesh kumar gowd | 3- Completed
sprint 2 ( 16/2/26) | sprint 2 (16/2/26) | girees_K_233 & ganesh_J_232 | I want to detect the type of document (Aadhaar / PAN / Passport) so that the correct verification flow is applied.Worked on the document detection model | MUST HAVE | Labeled document images | A Gireesh kumar gowd & Ganesh Jalkote | 3- Completed
sprint 3 ( 16/2/26) | sprint 3 (16/2/26) | girees_K_233 | I want to extract text from identity documents using openbharathocr so that user details can be captured automatically.(used Claude AI so that user details can be captured accurately for verification and stored in json files for training) | MUST HAVE | Labeled document images | A Gireesh kumar gowd | 3- Completed
Sprint 4 (22/02/26) | Sprint 4 (22/02/26) | kdhari_N_225 | I want to contribute on web development (interface) so i want to create an login and register pages . | MUST HAVE | Database setup | Kedhari Navya | 3- Completed
Sprint 5 (26/02/26) | Sprint 5 (26/02/26) | kurnoo_S_247, mahala_P_241, sai_M_240 | I want to develop a verification page after login so that users can upload and verify their documents. | MUST HAVE | Login & Register pages | Kurnoothala Sai Pragna,Mahalakshmi, sai madhumitha | 3- Completed
Sprint 6 (9/03/26 ) | Sprint 6 (9/03/26 ) | girees_K_233 | I want to build 3 Graph Neural Network (GNN) models to analyze relationships between PAN records , Aadhar records , passport records (seperately ) so that suspicious or anomalous identities can be detected automatically during KYC verification. | MUST HAVE | Extracted PAN records, Aadhaar records , passport records in .json file | A Gireesh kumar gowd | 3- Completed
Sprint 7 (11/03/26) | Sprint 7 (11/03/26) | pallap_A_239 | i want to work on a landing page as a part of frontend development, i wanted to create a innovative landing page for my project | MUST HAVE | as i worked on the landing page i have no dependencies. | Pallapu Akhila | 3- Completed
Sprint 8 (14/03/26) | Sprint 8 (14/03/26) | kdhari_N_225 | I want to work on backend, that is want to build the secure api service between frontend, backend and models. | MUST HAVE | Worked with MongoDB, Node js and Express js | Kedhari Navya | 3- Completed
Sprint 9 (20/03/26) | Sprint 9(20/03/26) | girees_K_233 | I want to integrate all the components (OCR, document classification, and GNN models) into a unified KYC verification pipeline so that the end-to-end verification flow works seamlessly. | MUST HAVE | GNN models, OCR extraction, Document classification, Frontend verification page | A Gireesh kumar gowd | 3- Completed
Sprint 10 (22/03/26) | Sprint 10 (22/03/26) | girees_K_233 | I want to refine and update the frontend and backend after integration so that the complete KYC verification system becomes functional and works accurately | MUST HAVE | Integrated KYC pipeline, GNN models, OCR extraction, Secure API (Backend), Verification page (Frontend) , DB | A Gireesh kumar gowd | 3- Completed
Sprint 11 (22/03/26) | Sprint 11 (22/03/26) | ankush_S_228 | I want to build the Document Forgery Detection Module which takes a template document image and outputs a forgery likelihood score. | MUST HAVE | A real adhaar card , pan card and passport document image to be used as a template. | Ankush S | 3- Completed
Sprint 12 (23/03/26) | Sprint 12 (23/03/26) | ankush_S_229 | I want to integrate the Document Forgery Detection Model into the backend with the KYC classifier and GNN models | MUST HAVE | Completed Document Forgery detection model | Ankush S | 3- Completed
Sprint 13 (23/03/26) | Sprint 13 (23/03/26) | gireesh_K_233 | i want to create a ppt for the project | SHOULD HAVE | complete knowledge about project | A Gireesh kumar gowd | 3- Completed
Sprint 14 (25/03/26) | Sprint 14 (25/03/26) | sannid_D_231 | i want to deploy the project on cloud | MUST HAVE | completed project | Sannidhi Sriram | 3- Completed
Sprint 15 (26/03/26) | Sprint 15(26/03/26) | gireesh_K_233 | i have implemented my idea of including Blockchain into this project | MUST HAVE | Verified kyc document data , metamask wallet, deployed smart contract, issued verifiers | A Gireesh kumar gowd | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG ¦ 10/02/2026 ¦ Image Data Collection
girees_K_233 | T1-01 | Set up Roboflow workspace and project configuration | 10/02/26 | 10/02/26 | A Gireesh Kumar Gowd | Setup | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T1-02 | Collect and upload Aadhaar card images to Roboflow | 10/02/26 | 10/02/26 | A Gireesh Kumar Gowd | Data Collection | Completed | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T1-03 | Collect and upload PAN card images to Roboflow | 10/02/26 | 10/02/26 | A Gireesh Kumar Gowd | Data Collection | Completed | 3 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T1-04 | Collect and upload Passport images to Roboflow | 10/02/26 | 10/02/26 | A Gireesh Kumar Gowd | Data Collection | Completed | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T1-05 | Label and annotate all document images in Roboflow | 10/02/26 | 10/02/26 | A Gireesh Kumar Gowd | Annotation | Completed | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG ¦ 16/02/2026 ¦ Document Type Detection Model
girees_K_233 & ganesh_J_232 | T2-01 | Prepare and export labeled dataset from Roboflow | 16/02/26 | 16/02/26 | Gireesh Kumar Gowd & Ganesh Jalkote | Development | Completed | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 & ganesh_J_232 | T2-02 | Design and configure document classification model architecture | 16/02/26 | 16/02/26 | Gireesh Kumar Gowd & Ganesh Jalkote | Development | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 & ganesh_J_232 | T2-03 | Train document type detection model (Aadhaar / PAN / Passport) | 16/02/26 | 16/02/26 | Gireesh Kumar Gowd & Ganesh Jalkote | Training | Completed | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 & ganesh_J_232 | T2-04 | Evaluate model accuracy and fine-tune hyperparameters | 16/02/26 | 16/02/26 | Gireesh Kumar Gowd & Ganesh Jalkote | Testing | Completed | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG ¦ 16/02/2026 ¦ OCR Text Extraction
girees_K_233 | T3-01 | Research and integrate OpenBharatOCR library | 16/02/26 | 16/02/26 | A Gireesh Kumar Gowd | Research | Completed | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T3-02 | Implement OCR pipeline for Aadhaar card field extraction | 16/02/26 | 16/02/26 | A Gireesh Kumar Gowd | Development | Completed | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T3-03 | Implement OCR pipeline for PAN card field extraction | 16/02/26 | 16/02/26 | A Gireesh Kumar Gowd | Development | Completed | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T3-04 | Integrate Claude AI for structured field capture and validation | 16/02/26 | 16/02/26 | A Gireesh Kumar Gowd | Integration | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T3-05 | Export extracted fields to JSON files for model training | 16/02/26 | 16/02/26 | A Gireesh Kumar Gowd | Development | Completed | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG ¦ 22/02/2026 ¦ Login & Register Pages
kdhari_N_225 | T4-01 | Design UI wireframes for login and register pages | 22/02/26 | 22/02/26 | Kedhari Navya | UI/UX Design | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
kdhari_N_225 | T4-02 | Set up MongoDB database schema and user model | 22/02/26 | 22/02/26 | Kedhari Navya | Database | Completed | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
kdhari_N_225 | T4-03 | Develop user registration page with form validation | 22/02/26 | 22/02/26 | Kedhari Navya | Frontend Dev | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
kdhari_N_225 | T4-04 | Develop login page with authentication logic | 22/02/26 | 22/02/26 | Kedhari Navya | Frontend Dev | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
kdhari_N_225 | T4-05 | End-to-end testing of login and register flow | 22/02/26 | 22/02/26 | Kedhari Navya | Testing | Completed | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG ¦ 26/02/2026 ¦ Document Verification Page
kurnoo_S_247 | T5-01 | Design document upload & verification page layout | 26/02/26 | 26/02/26 | Kurnoothala Sai Pragna | UI/UX Design | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
mahala_P_241 | T5-02 | Implement file upload component with document preview | 26/02/26 | 26/02/26 | Mahalakshmi | Frontend Dev | Completed | 3 | 3 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sai_M_240 | T5-03 | Connect verification page to backend API endpoints | 26/02/26 | 26/02/26 | Sai Madhumitha | Integration | Completed | 4 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
kurnoo_S_247 | T5-04 | Display KYC verification results dynamically on frontend | 26/02/26 | 26/02/26 | Kurnoothala Sai Pragna | Frontend Dev | Completed | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
mahala_P_241 | T5-05 | Test document upload and verification workflow | 26/02/26 | 26/02/26 | Mahalakshmi | Testing | Completed | 2 | 3 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG ¦ 09/03/2026 ¦ GNN Anomaly Detection Models
girees_K_233 | T6-01 | Design GNN architecture for PAN record anomaly detection | 09/03/26 | 09/03/26 | A Gireesh Kumar Gowd | Development | Completed | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T6-02 | Build and train GNN model on extracted PAN JSON records | 09/03/26 | 09/03/26 | A Gireesh Kumar Gowd | Training | Completed | 3 | 3 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T6-03 | Build and train GNN model on extracted Aadhaar JSON records | 09/03/26 | 09/03/26 | A Gireesh Kumar Gowd | Training | Completed | 3 | 2 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T6-04 | Build and train GNN model on extracted Passport JSON records | 09/03/26 | 09/03/26 | A Gireesh Kumar Gowd | Training | Completed | 2 | 3 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T6-05 | Normalize GNN output and validate anomaly score range (0–6) | 09/03/26 | 09/03/26 | A Gireesh Kumar Gowd | Testing | Completed | 3 | 2 | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 7 BACKLOG ¦ 11/03/2026 ¦ Landing Page
pallap_A_239 | T7-01 | Design and wireframe innovative landing page layout | 11/03/26 | 11/03/26 | Pallapu Akhila | UI/UX Design | Completed | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
pallap_A_239 | T7-02 | Develop hero section with animations and project overview | 11/03/26 | 11/03/26 | Pallapu Akhila | Frontend Dev | Completed | 3 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
pallap_A_239 | T7-03 | Add features section, team details, and navigation links | 11/03/26 | 11/03/26 | Pallapu Akhila | Frontend Dev | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
pallap_A_239 | T7-04 | Make landing page fully responsive for mobile and tablet | 11/03/26 | 11/03/26 | Pallapu Akhila | Frontend Dev | Completed | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 8 BACKLOG ¦ 14/03/2026 ¦ Secure Backend API Service
kdhari_N_225 | T8-01 | Set up Node.js and Express.js project structure | 14/03/26 | 14/03/26 | Kedhari Navya | Setup | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
kdhari_N_225 | T8-02 | Implement JWT-based authentication middleware | 14/03/26 | 14/03/26 | Kedhari Navya | Development | Completed | 3 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
kdhari_N_225 | T8-03 | Build REST API endpoints for KYC document verification | 14/03/26 | 14/03/26 | Kedhari Navya | Development | Completed | 6 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
kdhari_N_225 | T8-04 | Configure MongoDB connection and data schemas | 14/03/26 | 14/03/26 | Kedhari Navya | Database | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
kdhari_N_225 | T8-05 | Test all API endpoints and resolve integration bugs | 14/03/26 | 14/03/26 | Kedhari Navya | Testing | Completed | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 9 BACKLOG ¦ 20/03/2026 ¦ End-to-End KYC Pipeline Integration
girees_K_233 | T9-01 | Design unified KYC verification pipeline architecture | 20/03/26 | 20/03/26 | A Gireesh Kumar Gowd | Architecture | Completed | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T9-02 | Integrate OCR extraction module into pipeline | 20/03/26 | 20/03/26 | A Gireesh Kumar Gowd | Integration | Completed | 3 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T9-03 | Integrate document classification model into pipeline | 20/03/26 | 20/03/26 | A Gireesh Kumar Gowd | Integration | Completed | 4 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T9-04 | Integrate all 3 GNN models into verification pipeline | 20/03/26 | 20/03/26 | A Gireesh Kumar Gowd | Integration | Completed | 3 | 4 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T9-05 | End-to-end testing of complete KYC pipeline flow | 20/03/26 | 20/03/26 | A Gireesh Kumar Gowd | Testing | Completed | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 10 BACKLOG ¦ 22/03/2026 ¦ System Refinement & Stabilisation
girees_K_233 | T10-01 | Refine frontend UI based on post-integration feedback | 22/03/26 | 22/03/26 | A Gireesh Kumar Gowd | Frontend Dev | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T10-02 | Fix MongoDB schema validation blocking document saves | 22/03/26 | 22/03/26 | A Gireesh Kumar Gowd | Bug Fix | Completed | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T10-03 | Optimise backend API response times and error handling | 22/03/26 | 22/03/26 | A Gireesh Kumar Gowd | Development | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
girees_K_233 | T10-04 | System-wide functional verification and regression testing | 22/03/26 | 22/03/26 | A Gireesh Kumar Gowd | Testing | Completed | 3 | 3 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 11 BACKLOG ¦ 22/03/2026 ¦ Document Forgery Detection Module
ankush_S_228 | T11-01 | Collect real Aadhaar, PAN & Passport images as templates | 22/03/26 | 22/03/26 | Ankush S | Data Collection | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ankush_S_228 | T11-02 | Design forgery detection algorithm and scoring logic | 22/03/26 | 22/03/26 | Ankush S | Development | Completed | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ankush_S_228 | T11-03 | Build model comparing uploaded document against template | 22/03/26 | 22/03/26 | Ankush S | Development | Completed | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ankush_S_228 | T11-04 | Validate forgery likelihood score on sample documents | 22/03/26 | 22/03/26 | Ankush S | Testing | Completed | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 12 BACKLOG ¦ 23/03/2026 ¦ Forgery Detection Integration
ankush_S_229 | T12-01 | Integrate forgery detection module into backend KYC service | 23/03/26 | 23/03/26 | Ankush S | Integration | Completed | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ankush_S_229 | T12-02 | Connect forgery module with GNN classifier in pipeline | 23/03/26 | 23/03/26 | Ankush S | Integration | Completed | 4 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ankush_S_229 | T12-03 | Resolve package version conflicts (TensorFlow, OpenCV, OCR) | 23/03/26 | 23/03/26 | Ankush S | Bug Fix | Completed | 3 | 3 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ankush_S_229 | T12-04 | End-to-end test of integrated forgery + KYC pipeline | 23/03/26 | 23/03/26 | Ankush S | Testing | Completed | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 13 BACKLOG ¦ 23/03/2026 ¦ Project Presentation (PPT)
gireesh_K_233 | T13-01 | Outline PPT structure and create slide plan | 23/03/26 | 23/03/26 | A Gireesh Kumar Gowd | Documentation | Completed | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
gireesh_K_233 | T13-02 | Create slides: problem statement, architecture & models | 23/03/26 | 23/03/26 | A Gireesh Kumar Gowd | Documentation | Completed | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
gireesh_K_233 | T13-03 | Add demo screenshots, results and final review | 23/03/26 | 23/03/26 | A Gireesh Kumar Gowd | Documentation | Completed | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 14 BACKLOG ¦ 25/03/2026 ¦ Cloud Deployment (AWS)
sannid_D_231 | T14-01 | Configure AWS EC2 instance and install all dependencies | 25/03/26 | 25/03/26 | Sannidhi Sriram | DevOps | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sannid_D_231 | T14-02 | Deploy frontend React app on AWS S3 static hosting | 25/03/26 | 25/03/26 | Sannidhi Sriram | DevOps | Completed | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sannid_D_231 | T14-03 | Deploy backend Node.js server on EC2 with PM2 | 25/03/26 | 25/03/26 | Sannidhi Sriram | DevOps | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sannid_D_231 | T14-04 | Deploy ML Flask service on EC2 with Python venv via PM2 | 25/03/26 | 25/03/26 | Sannidhi Sriram | DevOps | Completed | 5 | 5 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sannid_D_231 | T14-05 | Fix CORS mismatch between S3 frontend and EC2 backend | 25/03/26 | 25/03/26 | Sannidhi Sriram | Bug Fix | Completed | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
sannid_D_231 | T14-06 | Handle Non-KYC document edge cases in deployed system | 25/03/26 | 25/03/26 | Sannidhi Sriram | Testing | Completed | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 15 BACKLOG ¦ 26/03/2026 ¦ Blockchain Integration
gireesh_K_233 | T15-01 | Design blockchain architecture and smart contract logic for KYC | 26/03/26 | 26/03/26 | A Gireesh Kumar Gowd | Architecture | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
gireesh_K_233 | T15-02 | Develop and unit-test smart contract for KYC record storage | 26/03/26 | 26/03/26 | A Gireesh Kumar Gowd | Development | Completed | 5 | 5 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
gireesh_K_233 | T15-03 | Deploy smart contract on-chain and configure MetaMask wallet | 26/03/26 | 26/03/26 | A Gireesh Kumar Gowd | DevOps | Completed | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
gireesh_K_233 | T15-04 | Integrate blockchain verification layer into KYC backend | 26/03/26 | 26/03/26 | A Gireesh Kumar Gowd | Integration | Completed | 6 | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
gireesh_K_233 | T15-05 | Issue verifier credentials and perform blockchain KYC flow test | 26/03/26 | 26/03/26 | A Gireesh Kumar Gowd | Testing | Completed | 3 | 3 | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Standup meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 16 | OCR misreading fields in low-quality document images | Applied preprocessing (grayscale, thresholding) and improved OCR pipeline — accuracy improved but not fully resolved
Sprint 6 | Day 37 | GNN anomaly score exceeding expected range (0–6), producing values 120–400 | Normalised output using scaling and adjusted activation function — model outputs now within expected range
Sprint 9 | Day 49 | Groq LLM occasionally parsing incorrect fields from documents | Added prompt tuning and validation checks for extracted fields — needs further refinement
Sprint 10 | Day 50 | MongoDB schema validation blocking saves due to strict enum and max value constraints | Relaxed schema rules and updated validation logic — data insertion working correctly
Sprint 12 | Day 53 | Package version conflicts between TensorFlow, OpenCV, and OpenBharatOCR | Resolved by fixing compatible versions, creating requirements.txt and using virtual environment — stable environment achieved
Sprint 14 | Day 55 | Frontend api.js calling ML service directly (detectDocumentType, extractOCRText) bypassing backend — CORS errors and broken auth | Removed all direct ML API functions from api.js; single entry point verifyDocument() routes all calls through backend /api/kyc/verify
Sprint 14 | Day 56 | Backend Node.js server binding to 127.0.0.1 only — external HTTP requests from browser and other services refused on port 5000 | Changed app.listen(PORT) to app.listen(PORT, '0.0.0.0') in server.js to bind to all network interfaces — external access confirmed working
Sprint 14 | Day 57 | Frontend on AWS S3 returning CORS error when calling backend EC2 API — Access-Control-Allow-Origin mismatch | Updated CORS config in server.js to include S3 bucket URL in allowed origins array; restarted backend via pm2 — login, upload and verification working from public URL
Sprint 14 | Day 58 | PM2 launches ML Flask service using system Python 3.12 which lacks ML dependencies — crashes with ModuleNotFoundError: numpy | Changed PM2 start command to use venv Python interpreter explicitly — ML service running stably under PM2, all models loaded successfully
Sprint 14 | Day 59 | Invalid documents (non-KYC images) uploaded by users — system had no graceful handling, causing backend crashes or malformed responses | ML service returns document_type 'Non-KYC Document' for unrecognised images; frontend displays appropriate result state — no crashes observed

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-10-02 | 2026-10-02 | A Gireesh Kumar Gowd | Use structured annotation guidelines from the start | Collecting images without quality checks | Leveraging Roboflow for dataset management | Created a quality checklist for all future image uploads
2 | Sprint 2 | 16/02/2026 | 16/02/2026 | A Gireesh Kumar Gowd & Ganesh Jalkote | Share model training progress daily between team members | Working in silos without syncing on dataset preparation | Collaborating on model evaluation and fine-tuning | Set up shared experiment tracking log for model metrics
3 | Sprint 3 | 16/02/2026 | 16/02/2026 | A Gireesh Kumar Gowd | Add fallback logic when OCR confidence is low | Relying solely on OpenBharatOCR without a validation layer | Using Claude AI for structured field extraction and accuracy | Added confidence threshold check; low-confidence fields flagged for review
4 | Sprint 4 | 22/02/2026 | 22/02/2026 | Kedhari Navya | Write unit tests for each form validation rule | Skipping database schema review before building UI | Following component-based frontend development | Added schema review as a mandatory step before UI work
5 | Sprint 5 | 26/02/2026 | 26/02/2026 | Kurnoothala Sai Pragna, Mahalakshmi, Sai Madhumitha | Define API contracts before starting frontend integration | Developing frontend without finalised backend endpoints | Splitting UI, integration and testing across team members | Created a shared API contract document before coding began
6 | Sprint 6 | 2026-09-03 | 2026-09-03 | A Gireesh Kumar Gowd | Validate model output ranges with unit tests before integration | Assuming model outputs are within range without verification | Training separate GNN models per document type for accuracy | Added output range assertions to GNN model evaluation pipeline
7 | Sprint 7 | 2026-11-03 | 2026-11-03 | Pallapu Akhila | Test responsiveness on mobile devices during development | Designing only for desktop and fixing mobile issues at the end | Building visually engaging and innovative UI components | Adopted mobile-first design approach for all frontend sprints
8 | Sprint 8 | 14/03/2026 | 14/03/2026 | Kedhari Navya | Document all API endpoints in a shared README as they are built | Binding server to localhost only without considering deployment | Using Express middleware for modular and reusable route handling | Updated server.js to bind to 0.0.0.0 for external access; added API docs
9 | Sprint 9 | 20/03/2026 | 20/03/2026 | A Gireesh Kumar Gowd | Run integration smoke tests after each component is connected | Integrating all components at once without incremental testing | Maintaining a clear pipeline architecture diagram for reference | Added a step-by-step integration checklist for future sprints
10 | Sprint 10 | 22/03/2026 | 22/03/2026 | A Gireesh Kumar Gowd | Involve the full team in regression testing after major changes | Making schema changes without notifying dependent services | Conducting thorough end-to-end verification after each fix | Introduced a change-notification protocol for schema and API updates
11 | Sprint 11 | 22/03/2026 | 22/03/2026 | Ankush S | Use a versioned template store for forgery reference images | Hardcoding template image paths in the detection module | Building modular detection components for easy reuse | Moved templates to a configurable directory with version control
12 | Sprint 12 | 23/03/2026 | 23/03/2026 | Ankush S | Maintain a requirements.txt and use virtual environments from sprint 1 | Installing packages globally causing version conflicts across modules | Testing the integrated pipeline on multiple document types | Created requirements.txt and venv setup guide for all team members
13 | Sprint 13 | 23/03/2026 | 23/03/2026 | A Gireesh Kumar Gowd | Maintain running notes throughout the project for easy PPT creation | Waiting until the end to document results and system design | Summarising each sprint outcome for use in final presentation | Added a project diary section to the shared repo for ongoing notes
14 | Sprint 14 | 25/03/2026 | 25/03/2026 | Sannidhi Sriram | Test CORS and network configurations locally before cloud deployment | Assuming localhost configurations will work directly on cloud | Using PM2 for reliable process management in production | Created a pre-deployment checklist covering CORS, ports, and env variables
15 | Sprint 15 | 26/03/2026 | 26/03/2026 | A Gireesh Kumar Gowd | Write smart contract unit tests before deploying on-chain | Deploying untested contracts directly to the blockchain | Innovating beyond requirements to add real-world value | Added Hardhat test suite for smart contract before mainnet deployment